Weld County Public Health & Environment

MHU Data Systems Assessment: Project Logic Model

| INPUTS What we have and who is involved |  | ACTIVITIES What we are doing |  | OUTPUTS What we will produce |  | SHORT-TERM OUTCOMES Changes in 1 to 3 months |  | LONG-TERM OUTCOMES Changes by end of project |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| People - Selorm Buaka -PHS Intern - Shaun May -Public Health Services Director - Olivia Egen- Community Director - Shanti Sanchez and Jennifer Robinson - PHS mobile unit leads - Cynthia Horn, - Chief Nursing Officer - Sonya Oster -PHS Business Operations Manager - CH: Kelly, Olga - EH: Cassie Thieson - Jason Chessher- Executive Director - External data systems consultant (potential) Data - MHU Tracking Sheets 2025 (54 events) and 2026 (31 events) - Athena EMR -PHS individual-level patient records - Heart of Weld data - CH cardiovascular and pre-diabetes - screening, CDC-certified program, CHW-run - Lead Explore Prevention Program - EH only MHU service - Client satisfaction survey (to be located) Frameworks and Resources - FCSM Framework - 11 dimensions, 3 domains - Parker et al. 2024 - CDC data quality framework - OneDrive shared project folder Support Needed from Teams - 90-minute interview with each division team - Access to division data and reporting documents - Participation in at least one field event | → | Phase 1 : Assessment - Project Kickoff PHS Outreach Meeting, May 25, 11am - Set up OneDrive project folder with shared edit access - Audit 2025 and 2026 data across all 11 FCSM dimensions - Conduct structured interviews with PHS, CH, and EH - Build data dictionary from interview definitions - Assess address quality and geocoding readiness - Map grant reporting pipelines for all three divisions - Locate and assess the client satisfaction survey - Attend at least one field event to observe directly Phase 2: Recommendations - Score each division on all 11 FCSM dimensions - Produce written assessment report with evidence - Deliver prioritized recommendations with cost-benefit - Brief external consultant once scope is confirmed Phase 3: Dashboard Development - Design and build internal dashboard for teams - Design and build external dashboard for leadership - Produce documentation and staff guidance - Present final work to the Executive Director | → | Documents Produced - Interview guides- PHS, CH, EH - FCSM scorecard- 11 dimensions rated per division - Data dictionary- written definitions per division - Assessment report with findings and evidence - Recommendations with cost-benefit analysis - Grant reporting pipeline map- all three divisions Dashboards Built - Internal -event trends, service counts, - location performance, hotspot analysis - External - who was served, where, what was done, - impact for board, commissioners, and funders Supporting Materials - Dashboard documentation and staff guidance | → | Data System - Written definitions agreed engagement, person served, - and screening across all three divisions - Address quality improves; events can be mapped - Services in notes get dedicated structured columns - CHW activity visible in Community Health data - EH attendance field standardized across divisions - Client survey located and linked to event-level data - Grant pipelines mapped, confidentiality confirmed - 2025 and 2026 data schema made consistent Reporting - Internal dashboard live for all division teams - Leadership has near-real-time MHU activity data | → | Program Capability - Program tells a credible, data-driven story of - who was served, where, and with what impact - Board and commissioners have real-time - accountability evidence via external dashboard - Hotspot analysis guides evidence-based deployment - Data system runs without manual quarterly reports Program Sustainability - Grant renewal backed by robust performance data - Program positioned for expansion - Systems designed to scale as services grow |

| Assumptions - Division teams engage openly and honestly in interviews - Access to all datasets and documents provided via OneDrive - Data gaps treated as system issues, not individual failures - Leadership acts on feasible, cost-effective recommendations - EH continues to participate in the MHU program - The client satisfaction survey exists and can be located |  | External Factors - Grant renewal timelines and funder reporting requirements - Staff capacity and availability across divisions - Potential involvement of external data systems consultant - Board and commissioner accountability reporting expectations - County IT constraints on dashboard tools and licensing |
| --- | --- | --- |